## Actions & Commitments
Last Update: | 2022-02-09
Update Time: | 0:13
Updater: | Nahom | [7 empty] | Add any timely updates or comments along this timeline for long opened actions
Priority | Owner | Task | For Deliverable | Category | Status | Opened | Due | Closed | 2018-09-28 | 2018-09-29 | 2018-09-30 | 2018-10-01 | 2018-10-02 | 2018-10-05 | 2018-10-06 | 2018-10-07 | 2018-10-08 | 2018-10-09 | 2018-10-12 | 2018-10-13 | 2018-10-14 | 2018-10-15 | 2018-10-16 | 2018-10-19 | 2018-10-20 | 2018-10-21 | 2018-10-22 | 2018-10-23 | 2018-10-26 | 2018-10-27 | 2018-10-28 | 2018-10-29 | 2018-10-30 | 2018-11-02 | 2018-11-03 | 2018-11-04 | 2018-11-05 | 2018-11-06 | 2018-11-09 | 2018-11-10 | 2018-11-11 | 2018-11-12 | 2018-11-13 | 2018-11-16 | 2018-11-17 | 2018-11-18 | 2018-11-19 | 2018-11-20 | 2018-11-23 | 2018-11-24 | 2018-11-25 | 2018-11-26 | 2018-11-27 | 2018-11-30 | 2018-12-01 | 2018-12-02 | 2018-12-03 | 2018-12-04 | 2018-12-07 | 2018-12-08 | 2018-12-09 | 2018-12-10 | 2018-12-11 | 2018-12-14 | 2018-12-15 | 2018-12-16 | 2018-12-17 | 2018-12-18 | 2018-12-21 | 2018-12-22 | 2018-12-23 | 2018-12-24 | 2018-12-25 | 2018-12-28 | 2018-12-29 | 2018-12-30 | 2018-12-31 | 2019-01-01 | 2019-01-04 | 2019-01-05 | 2019-01-06 | 2019-01-07 | 2019-01-08 | 2019-01-11 | 2019-01-12 | 2019-01-13 | 2019-01-14 | 2019-01-15 | 2019-01-18 | 2019-01-19 | 2019-01-20 | 2019-01-21 | 2019-01-22 | 2019-01-25 | 2019-01-26 | 2019-01-27 | 2019-01-28 | 2019-01-29 | 2019-02-01 | 2019-02-02 | 2019-02-03 | 2019-02-04 | 2019-02-05 | 2019-02-08 | 2019-02-09 | 2019-02-10 | 2019-02-11 | 2019-02-12 | 2019-02-15 | 2019-02-16 | 2019-02-17 | 2019-02-18 | 2019-02-19 | 2019-02-22 | 2019-02-23 | 2019-02-24 | 2019-02-25 | 2019-02-26
| Richard | (sample) Just a dummy task to demonstrate an entry |  | 50-PROJ MGMT | 2-CLOSED | 2018-01-19 | 2018-01-22 | 2018-01-20 | Opened during morning scrum |  |  | talked to product owner and did dummy task. All is OK, closing
| Coady | (sample) Update the database to use views |  | 03-DEVELOPMENT | 1-OPEN | 2018-01-26 | 2018-01-26 | [6 empty] | Raised during scrum. Should be done same day. |  |  | Ran into environmental issues. Still working on it, but likely won't be done until Wed.
| Noah | Find fix for JudgeO |  | 11-DEFECTS | 1-OPEN | 2022-12-03
| Nahom | Send out meeting minutes |  |  | 2-CLOSED | 2021-12-07 |  | 2022-12-08
| Nahom | Update the backlog with the new priorities |  |  | 2-CLOSED | 2022-12-07 |  | 2022-12-08
| Nahom | Add the acceptance criteria for the decisions |  |  | 2-CLOSED | 2022-12-07 |  | 2022-12-08
| Nahom | Daily Scrum |  |  | 2-CLOSED | 2022-02-09 |  | 2022-02-09
| Nahom | Send out meeting minutes |  |  | 2-CLOSED | 2022-02-09 |  | 2022-02-09
Note on B1: richard: Update this every time the spreadsheet is updated so we know last modification times stamp

## Retrospective
Last Update: | 12-03-2021
Update Time: | 2:30pm
Updater: | Noah
Retrospective, Sprint # | Date Added | Scribe | Team member | Went Well | Not Well | Lessons Learnt | What bugs us/mysterious?
1 | 12-03-2021 | Noah | Emanuelle | We did much better at times that we were meeting. Scrums were good and consise. Better PR's and inspecting. We caught a lot | Estimation was just okay, we should be more careful in merging | Don't cut corners when going about the process | Test cases that the teacher can test
|  | Noah | Alex | Scrums were much better, getting everything done we managed to get most things done. Better reviewing and following the process | We Ignored priorities of tasks at first, we shoudn't have | Be more skeptical when following the process and think about more cases when checking in a change | C#
|  | Noah | Zhaojiang | Communication was better, better discussions when we had questions. | Be better in testing your work before you push it, it was only okay, often more bugs were created when one bug was fixed | Don't prioritize quick fixes over better, longer ones. | Nothin to add
|  | Noah | Arsen | Much better job reviewing our code with the PR's. We followed more of the coding standards. Thought the tasking was fine. | Remaining work was not always being updated | Communication on PR's should be better | DB design
|  | Noah | Nahom | Splitting tasks up went well, PR's was better, better reviewing. Communication was up. | Too many DB changes, we didn't do a good job of doing them | Better tasking, I think it should be assinged to people, not the other way around. Reviews shouldn't be rushed. Break down bigger tasks. | Create/edit page workflow
|  | Noah | Abe | Communitation was better, same as others. People are more proactive in doing work. | Could have had better time budgets. Bit of a cruch at the very end | Take the priority tasks | DB design
|  | Noah | Noah | Agrees with everybody | Could have had better time budgets. Bit of a cruch at the very end | Nothin to add | Funky test cases
Note on B1: richard: Update this every time the spreadsheet is updated so we know last modification times stamp
Note on B6: richard: Update this every time the spreadsheet is updated so we know last modification times stamp

## Lessons Learnt (Team)
Last Update: | 2022-01-31
Update Time: | 2:01PM
Updater: | Alex
Lesson # | Date Added | By | Lessons Learnt
1 | 12-03-2021 | Noah | Need better organization and a stronger backlog, as well as not to forget testing.
2 | 12-03-2021 | Nahom | Review wording and spelling before closing task
3 | 12-03-2021 | Emmanuelle | When something doesn't work, move on or try something simpler.
4 | 12-03-2021 | Alex | Do some testing for each task and include testing time in the estimate. Make sure we have a strong backlog.
5 | 12-03-2021 | Abe | Assign different things to everyone so not only one person is being an expert in a single area.
6 | 12-03-2021 | Zhaojiang | Don't spend too much time on one thing.
7 | 12-03-2021 | Arsen | Before completing your ticket, do testing.
Note on B1: richard: Update this every time the spreadsheet is updated so we know last modification times stamp
Note on B6: richard: Update this every time the spreadsheet is updated so we know last modification times stamp

## ATTENDANCE
 | time axis 2018-09-28 to 2019-02-26
Meeting Description | bar: 2018-09-28 to 2018-11-20
Scrum | 2018-09-28: MemberA, MemberB, MemberC, …
Ragnar Paulson | 2018-09-28: OoO; 2018-09-29: x; 2018-09-30: x; 2018-10-02: N/A; 2018-10-06: N/A; 2018-10-08: N/A; 2018-10-13: N/A; 2018-10-15: N/A; 2018-10-19: N/A; 2018-10-20: N/A; 2018-10-22: N/A

## PARAMETERS
STATES
0-NEW
1-OPEN
2-CLOSED
3-BLOCKED
VARIOUS
INFO
MONITOR
TEAM
Noah
Alex
Emmanuelle
Abe
Nahom
Arsen
Zhaojiang
TOPIC
01-REQ
02-ARCH
03-DEVELOPMENT
05-TESTING
07-SCRIPTS/UTILITIES
11-DEFECTS
12-HANDOVER
14-PROD READINESS
19-ACCEPTANCE
20-DOCUMENTATION/TRAINING
50-PROJ MGMT
51-ISSUES\RISKS
90-ENVIRONMENT
99-MISC