## Actions & Commitments
Last Update: | 2022-02-09
Update Time: | 0:13
Updater: | Nahom | [7 empty] | Add any timely updates or comments along this timeline for long opened actions
Priority | Owner | Task | For Deliverable | Category | Status | Opened | Due | Closed | 2018-09-28 | 2018-09-29 | 2018-09-30 | 2018-10-01 | 2018-10-02 | 2018-10-05 | 2018-10-06 | 2018-10-07 | 2018-10-08 | 2018-10-09 | 2018-10-12 | 2018-10-13 | 2018-10-14 | 2018-10-15 | 2018-10-16 | 2018-10-19 | 2018-10-20 | 2018-10-21 | 2018-10-22 | 2018-10-23 | 2018-10-26 | 2018-10-27 | 2018-10-28 | 2018-10-29 | 2018-10-30 | 2018-11-02 | 2018-11-03 | 2018-11-04 | 2018-11-05 | 2018-11-06 | 2018-11-09 | 2018-11-10 | 2018-11-11 | 2018-11-12 | 2018-11-13 | 2018-11-16 | 2018-11-17 | 2018-11-18 | 2018-11-19 | 2018-11-20 | 2018-11-23 | 2018-11-24 | 2018-11-25 | 2018-11-26 | 2018-11-27 | 2018-11-30 | 2018-12-01 | 2018-12-02 | 2018-12-03 | 2018-12-04 | 2018-12-07 | 2018-12-08 | 2018-12-09 | 2018-12-10 | 2018-12-11 | 2018-12-14 | 2018-12-15 | 2018-12-16 | 2018-12-17 | 2018-12-18 | 2018-12-21 | 2018-12-22 | 2018-12-23 | 2018-12-24 | 2018-12-25 | 2018-12-28 | 2018-12-29 | 2018-12-30 | 2018-12-31 | 2019-01-01 | 2019-01-04 | 2019-01-05 | 2019-01-06 | 2019-01-07 | 2019-01-08 | 2019-01-11 | 2019-01-12 | 2019-01-13 | 2019-01-14 | 2019-01-15 | 2019-01-18 | 2019-01-19 | 2019-01-20 | 2019-01-21 | 2019-01-22 | 2019-01-25 | 2019-01-26 | 2019-01-27 | 2019-01-28 | 2019-01-29 | 2019-02-01 | 2019-02-02 | 2019-02-03 | 2019-02-04 | 2019-02-05 | 2019-02-08 | 2019-02-09 | 2019-02-10 | 2019-02-11 | 2019-02-12 | 2019-02-15 | 2019-02-16 | 2019-02-17 | 2019-02-18 | 2019-02-19 | 2019-02-22 | 2019-02-23 | 2019-02-24 | 2019-02-25 | 2019-02-26
| Richard | (sample) Just a dummy task to demonstrate an entry |  | 50-PROJ MGMT | 2-CLOSED | 2018-01-19 | 2018-01-22 | 2018-01-20 | Opened during morning scrum |  |  | talked to product owner and did dummy task. All is OK, closing
| Coady | (sample) Update the database to use views |  | 03-DEVELOPMENT | 1-OPEN | 2018-01-26 | 2018-01-26 | [6 empty] | Raised during scrum. Should be done same day. |  |  | Ran into environmental issues. Still working on it, but likely won't be done until Wed.
| Noah | Find fix for JudgeO |  | 11-DEFECTS | 1-OPEN | 2022-12-03
| Nahom | Send out meeting minutes |  |  | 2-CLOSED | 2021-12-07 |  | 2022-12-08
| Nahom | Update the backlog with the new priorities |  |  | 2-CLOSED | 2022-12-07 |  | 2022-12-08
| Nahom | Add the acceptance criteria for the decisions |  |  | 2-CLOSED | 2022-12-07 |  | 2022-12-08
| Nahom | Daily Scrum |  |  | 2-CLOSED | 2022-02-09 |  | 2022-02-09
| Nahom | Send out meeting minutes |  |  | 2-CLOSED | 2022-02-09 |  | 2022-02-09
Note on B1: richard: Update this every time the spreadsheet is updated so we know last modification times stamp

## Retrospective
Last Update: | 12-03-2021
Update Time: | 2:30pm
Updater: | Noah
Retrospective, Sprint # | Date Added | Scribe | Team member | Went Well | Not Well | Lessons Learnt | What bugs us/mysterious?
1 | 12-03-2021 | Noah | Nahom | We got most of the func working, missing only a few things. Worked well as a team. Alex did well as APM. | make DB technical errors, which broke everything and Abe had to make fixes. Lack of testing. Z and Nahom having similar tasks | Before saying a tasks is done, review wording and spelling. Go deeper for reviews, before starting a task, maybe see if it overlaps with another. Rushed ordering for student, didn't code it in a good way
|  | Noah | Emanuelle | Most of our goals were mostly met, we were also always on track, it was clear who was doing what | Like Noah said, testing was lacking, we don’t have enough, there is a lot of error testing and validation that is missing. We communicate well, but eveybody knows their task, but often we don't always know what others are doing, it could've saved some work. | When something isn't working, don't bang your head for too long, when something doesn't work move on or do something simple. More visibility for other's tasks. Once a week, we can see the changes made by others.
|  | Noah | Alex | The backlog went well, organization was good, managing time with tasks went well, even with new ones. Getting better at completing tasks | At the start, very unorganzied, the backlog. Tough starting, and snowballed into some tasks being similar, other tasks not being needed. Sprint review, we only completed one of our user stories. | Do testing as part of each task. Include it in the estimate. Main lesson is everything stems from a weak backlog. All the problems. There has to be a strong backlog start, because we had to keep editing them.
|  | Noah | Abe | Everyone stayed focused on their tasks, but also helping othes on their tasks. Alex did a great job | The fact that I had to do much DB stuff, new tasks that came up were assigned to me, didn't have as much time to do the "Create Func" tasks | Agree with everything else. If things come up that aren't expected, don't assign them to the same person. Spent most of the time doing DB
|  | Noah | Zhaojiang | Teams power. When I didn't know how to do something, everybody helped. This is a very useful and team dynamics is very important. Learnt how to merge branches. | The branch merging didn't go well, often needed help with that. | Nothing to add. Just focused on teacher homepage, spent too much time on it.
|  | Noah | Arsen | Agrees with everything previously said. Did a good job helping others, making sure nobody gets left to add | Wish that I would've done more before the Sprint Review, as there were some bugs | As a team, testing is important, do testing before completing ticket. Asking to
|  | Noah | Noah | Not much new to add | Didn't do the acceptance criteria much, only at the end. Could have been done better | Nothing that hasn't been talked about. Test cases, backlog organization, ect | IIS not being able to talk to the API
Note on B1: richard: Update this every time the spreadsheet is updated so we know last modification times stamp
Note on B6: richard: Update this every time the spreadsheet is updated so we know last modification times stamp

## Lessons Learnt (Team)
Last Update: | 2022-01-31
Update Time: | 2:01PM
Updater: | Alex
Lesson # | Date Added | By | Lessons Learnt
1 | 12-03-2021 | Noah | Need better organization and a stronger backlog, as well as not to forget testing.
2 | 12-03-2021 | Nahom | Review wording and spelling before closing task
3 | 12-03-2021 | Emmanuelle | When something doesn't work, move on or try something simpler.
4 | 12-03-2021 | Alex | Do some testing for each task and include testing time in the estimate. Make sure we have a strong backlog.
5 | 12-03-2021 | Abe | Assign different things to everyone so not only one person is being an expert in a single area.
6 | 12-03-2021 | Zhaojiang | Don't spend too much time on one thing.
7 | 12-03-2021 | Arsen | Before completing your ticket, do testing.
Note on B1: richard: Update this every time the spreadsheet is updated so we know last modification times stamp
Note on B6: richard: Update this every time the spreadsheet is updated so we know last modification times stamp

## ATTENDANCE
 | time axis 2018-09-28 to 2019-02-26
Meeting Description | bar: 2018-09-28 to 2018-11-20
Scrum | 2018-09-28: MemberA, MemberB, MemberC, …
Ragnar Paulson | 2018-09-28: OoO; 2018-09-29: x; 2018-09-30: x; 2018-10-02: N/A; 2018-10-06: N/A; 2018-10-08: N/A; 2018-10-13: N/A; 2018-10-15: N/A; 2018-10-19: N/A; 2018-10-20: N/A; 2018-10-22: N/A

## PARAMETERS
STATES
0-NEW
1-OPEN
2-CLOSED
3-BLOCKED
VARIOUS
INFO
MONITOR
TEAM
Noah
Alex
Emmanuelle
Abe
Nahom
Arsen
Zhaojiang
TOPIC
01-REQ
02-ARCH
03-DEVELOPMENT
05-TESTING
07-SCRIPTS/UTILITIES
11-DEFECTS
12-HANDOVER
14-PROD READINESS
19-ACCEPTANCE
20-DOCUMENTATION/TRAINING
50-PROJ MGMT
51-ISSUES\RISKS
90-ENVIRONMENT
99-MISC