## Actions & Commitments
Last Update: | 2022-02-09
Update Time: | 0:13
Updater: | Nahom | [7 empty] | Add any timely updates or comments along this timeline for long opened actions
Priority | Owner | Task | For Deliverable | Category | Status | Opened | Due | Closed | 2018-09-28 | 2018-09-29 | 2018-09-30 | 2018-10-01 | 2018-10-02 | 2018-10-05 | 2018-10-06 | 2018-10-07 | 2018-10-08 | 2018-10-09 | 2018-10-12 | 2018-10-13 | 2018-10-14 | 2018-10-15 | 2018-10-16 | 2018-10-19 | 2018-10-20 | 2018-10-21 | 2018-10-22 | 2018-10-23 | 2018-10-26 | 2018-10-27 | 2018-10-28 | 2018-10-29 | 2018-10-30 | 2018-11-02 | 2018-11-03 | 2018-11-04 | 2018-11-05 | 2018-11-06 | 2018-11-09 | 2018-11-10 | 2018-11-11 | 2018-11-12 | 2018-11-13 | 2018-11-16 | 2018-11-17 | 2018-11-18 | 2018-11-19 | 2018-11-20 | 2018-11-23 | 2018-11-24 | 2018-11-25 | 2018-11-26 | 2018-11-27 | 2018-11-30 | 2018-12-01 | 2018-12-02 | 2018-12-03 | 2018-12-04 | 2018-12-07 | 2018-12-08 | 2018-12-09 | 2018-12-10 | 2018-12-11 | 2018-12-14 | 2018-12-15 | 2018-12-16 | 2018-12-17 | 2018-12-18 | 2018-12-21 | 2018-12-22 | 2018-12-23 | 2018-12-24 | 2018-12-25 | 2018-12-28 | 2018-12-29 | 2018-12-30 | 2018-12-31 | 2019-01-01 | 2019-01-04 | 2019-01-05 | 2019-01-06 | 2019-01-07 | 2019-01-08 | 2019-01-11 | 2019-01-12 | 2019-01-13 | 2019-01-14 | 2019-01-15 | 2019-01-18 | 2019-01-19 | 2019-01-20 | 2019-01-21 | 2019-01-22 | 2019-01-25 | 2019-01-26 | 2019-01-27 | 2019-01-28 | 2019-01-29 | 2019-02-01 | 2019-02-02 | 2019-02-03 | 2019-02-04 | 2019-02-05 | 2019-02-08 | 2019-02-09 | 2019-02-10 | 2019-02-11 | 2019-02-12 | 2019-02-15 | 2019-02-16 | 2019-02-17 | 2019-02-18 | 2019-02-19 | 2019-02-22 | 2019-02-23 | 2019-02-24 | 2019-02-25 | 2019-02-26
| Richard | (sample) Just a dummy task to demonstrate an entry |  | 50-PROJ MGMT | 2-CLOSED | 2018-01-19 | 2018-01-22 | 2018-01-20 | Opened during morning scrum |  |  | talked to product owner and did dummy task. All is OK, closing
| Coady | (sample) Update the database to use views |  | 03-DEVELOPMENT | 1-OPEN | 2018-01-26 | 2018-01-26 | [6 empty] | Raised during scrum. Should be done same day. |  |  | Ran into environmental issues. Still working on it, but likely won't be done until Wed.
| Noah | Find fix for JudgeO |  | 11-DEFECTS | 1-OPEN | 2022-12-03
| Nahom | Send out meeting minutes |  |  | 2-CLOSED | 2021-12-07 |  | 2022-12-08
| Nahom | Update the backlog with the new priorities |  |  | 2-CLOSED | 2022-12-07 |  | 2022-12-08
| Nahom | Add the acceptance criteria for the decisions |  |  | 2-CLOSED | 2022-12-07 |  | 2022-12-08
| Nahom | Daily Scrum |  |  | 2-CLOSED | 2022-02-09 |  | 2022-02-09
| Nahom | Send out meeting minutes |  |  | 2-CLOSED | 2022-02-09 |  | 2022-02-09
Note on B1: richard: Update this every time the spreadsheet is updated so we know last modification times stamp

## Retrospective
Last Update: | 12-03-2021
Update Time: | 2:30pm
Updater: | Noah
Retrospective, Sprint # | Date Added | Scribe | Team member | Went Well | Not Well | Lessons Learnt | What bugs us/mysterious? | Other
1 | 14-03-2022 | Noah | Abe | Feel that we did get work done. Communication was decent | Team morale was low, all the tasks sucked. | Trying to go through and work straight on takes away from the team effort. Didn't communicate as well as did my own thing for the most part. Do more communication as to what you're doing
|  | Noah | Emmanu | Code coverage went well. The delete User Story should be done, so we can close that. Ongoing from the other retro, but communication is better | Estimating wasn't great for test cases tasks.Team was sad | Unit tests. Learnt a lot about them. At first, tough to initally create them. Then things went smoother. Keep communicating with the team (mainly Noah). | DB, not the schema, but the DB changes. Things were breaking, and I thought It was my code, but it was really the DB changes.
|  | Noah | Alex | Reviewing is better, more thourough, code coverage. | Analysis of some tasks. | Having a solid understanding of the flow of a system would be better. Knowing what we need for the func to happen. Underestimating the hours. |  | Can we add an analysis phase so we don't go straight into development.
|  | Noah | Arsen | Agree with what everybody said. Process was followed better, documentation tasks | Agrees with Noah. Estimations. | Big thing was being the APM, learnt a lot about managing tasks. Making sure that people have the right tasks based on their strenghts. Communication with teammates
|  | Noah | Noah | Code coverage is awesome | Tasks completion | Estimates were terrible. Minimum add an hour for test cases.
|  | Noah | Z | Communication is better, helped a lot with tasks. | Return type ID, didn't know how to use JS to do that. Making changes to class diagram, Emanu couldn't understand my writing | Editing the DB was tough, first time touching the DB. Learnt a lot about how to change these things. Learnt how to add the right column. Need to learn how to communicate better. Sometimes when I start something I work on it on my own.
|  | Noah | Nahom | Good teamwork dynamics | My task. Spent too much time on it. Still doesn't work. | Agree with everyone. Especially with Noah about estimating, something that is on every "Lessons Learnt". Following the estimation process was better, but the execution wasn't there. Didn't plan my tasks well, just went for it. Scope leak for my task | Much confusion at the beginning of task. Had a solution, just no time to impliment it.
|  | Noah | Chris |  |  | We all have cognitive biases. "We think we understand". But we don’t. We should walk through the code before we make an estimate. Every task in the task board is precious. Don't worry about the other tasks. We think we communicate.
Note on B1: richard: Update this every time the spreadsheet is updated so we know last modification times stamp
Note on B6: richard: Update this every time the spreadsheet is updated so we know last modification times stamp

## Lessons Learnt (Team)
Last Update: | 2022-01-31
Update Time: | 2:01PM
Updater: | Alex
Lesson # | Date Added | By | Lessons Learnt
1 | 12-03-2021 | Noah | Need better organization and a stronger backlog, as well as not to forget testing.
2 | 12-03-2021 | Nahom | Review wording and spelling before closing task
3 | 12-03-2021 | Emmanuelle | When something doesn't work, move on or try something simpler.
4 | 12-03-2021 | Alex | Do some testing for each task and include testing time in the estimate. Make sure we have a strong backlog.
5 | 12-03-2021 | Abe | Assign different things to everyone so not only one person is being an expert in a single area.
6 | 12-03-2021 | Zhaojiang | Don't spend too much time on one thing.
7 | 12-03-2021 | Arsen | Before completing your ticket, do testing.
Note on B1: richard: Update this every time the spreadsheet is updated so we know last modification times stamp
Note on B6: richard: Update this every time the spreadsheet is updated so we know last modification times stamp

## ATTENDANCE
 | time axis 2018-09-28 to 2019-02-26
Meeting Description | bar: 2018-09-28 to 2018-11-20
Scrum | 2018-09-28: MemberA, MemberB, MemberC, …
Ragnar Paulson | 2018-09-28: OoO; 2018-09-29: x; 2018-09-30: x; 2018-10-02: N/A; 2018-10-06: N/A; 2018-10-08: N/A; 2018-10-13: N/A; 2018-10-15: N/A; 2018-10-19: N/A; 2018-10-20: N/A; 2018-10-22: N/A

## PARAMETERS
STATES
0-NEW
1-OPEN
2-CLOSED
3-BLOCKED
VARIOUS
INFO
MONITOR
TEAM
Noah
Alex
Emmanuelle
Abe
Nahom
Arsen
Zhaojiang
TOPIC
01-REQ
02-ARCH
03-DEVELOPMENT
05-TESTING
07-SCRIPTS/UTILITIES
11-DEFECTS
12-HANDOVER
14-PROD READINESS
19-ACCEPTANCE
20-DOCUMENTATION/TRAINING
50-PROJ MGMT
51-ISSUES\RISKS
90-ENVIRONMENT
99-MISC