## Team02
Sprint 1 for February 16th - March 9th.
# | Type | ID | Title | Estimate (hours)
1 | Task | 657 | Model test suites after CTP | 2
2 | Task | 660 | Add test cases for the ChallengeController | 2
3 | Task | 661 | Add test cases for the LoginController | 2
4 | Task | 662 | Add test cases for the StudentController | 2
5 | Task | 663 | Add test cases for the TeacherController | 2
6 | Task | 664 | Add test cases for the Challenge Model | 5
7 | Task | 665 | Add test cases for CurrentSession Model (Login) | 2
8 | Task | 666 | Add test cases for the Teacher Model | 2
9 | Bug | 553 | There should not be a "Delete" Primary Button on the Edit Challenge Page | 0.5
10 | Task | 596 | "Language" Dropdown should be disabled on the Edit Challenge Page | 0.5
11 | Bug | 598 | Remove "Cannot change language, there are test cases" error message | 0.5
12 | Bug | 586 | CSS on Create/Edit page is not responsive | 2.5
13 | Task | 587 | Create/Edit return type is not saved and is not present in the DB | 7
14 | Task | 589 | Out/In checkbox for Create/Edit Challenge should be just "In" and default to checked | 0.1
15 | Task | 592 | Add functionality for creating parameters AND test cases frontend in Create/Edit Challenge | 4
16 | Task | 593 | Parameters should be able to be arrays/objects in Create/Edit Challenge | 5
17 | Task | 655 | Add functionality for creating parameters in backend in Create/Edit Challenge | 5
18 | Task | 659 | Add functionality for creating test cases in backend in Create/Edit Challenge | 4
19 | Task | 668 | Discuss with Allan how to test "test cases" when creating a challenge | 2
20 | Bug | 603 | The Delete popup should display the number of people, and display the "last time attempted" in a more user friendly way | 0.3
21 | Bug | 605 | The delete confirmation message should display the Challenge title instead of the ID | 1
22 | Task | 87 | Get Judge0 to be hosted with docker on CSTEST | 10
23 | Task | 320 | Have indications if a language in a challenge is completed | 3
24 | Bug | 550 | All Challenges page for Students and Teachers is no longer responsive | 4
|  |  | Total (hours) | 68.4